NATIONAL DISASTER MANAGEMENT CENTRE
Department of Cooperative Governance

EXECUTIVE SUMMARY OF PORTFOLIO OF EVIDENCE

Sub-stream: Build Back Better (BBB)

Reporting Period: 21 September 2026 to 12 October 2026

Prepared by: Eng. Dingaan Mahlangu
Disaster Management Results Management Office Stream

# 1. Executive Summary

The reporting period covered September follow-up and the resumption of contracted work on 5 October. The principal documented outputs were the Limpopo strategic visit report, the NDMC–CSIR Project Specific Agreement (PSA) enhancement brief dated 23 September, the KRA-aligned October workplan dated 9 October and the updated September–October progress presentation prepared on 12 October. These outputs provide the basis for BBB technical refinement and coordinated recovery planning.

The previous contract ended on 3 September and renewal took effect on 5 October, leaving a gap from 4 September to 4 October. September contributions are included for continuity. Their inclusion does not establish approved billable hours. Technical implementation and completion claims will be updated against verified evidence.

# 2. Objectives for the Period

Consolidate Limpopo findings into the Disaster Management System Review and BBB priorities; develop technical and commercial inputs for the NDMC–CSIR PSA; and establish a dated October workplan against the four BBB KRAs. For 13–31 October, the objective is to refine standards and municipal tools while preparing environmental protection, community readiness and SEMS/ICS integration inputs.

# 3. Summary of Performance Targets

KRA 1: Resilient Infrastructure Standards and Upgrades. Refine hazard-resistant standards and compliance forms, and prepare three preliminary settlement upgrade design sheets. KRA 2: Environmental and Public Health Protections. Prepare wastewater, solid-waste, stormwater and air/water monitoring inputs for priority marginalized areas.

KRA 3: Community Preparedness, Education and Evacuation Readiness. Prepare household safety guidance, evacuation/drill checklists and last-mile warning procedures. KRA 4: Technical Integration, Response Documentation and DRM Review Alignment. Refine BBB framework and SEMS/ICS interfaces, consolidate CSIR requirements and compile monthly evidence. These are anticipated October outputs, not completed implementation results.

Actual: 0 hours; Estimated: 48 hours; Scheduled: 7 hours; Anticipated: 0 hours. Actual hours exclude estimates, scheduled durations and anticipated work.

October: 24 estimated retrospective hours plus 72 anticipated hours. The 96-hour ceiling is provisional. September scheduled hours are separate. The source report includes 24 hours for strategic report consolidation without a verified basis; this example classifies them as Estimated pending verification.

Previous contract ended 3 September; renewal took effect 5 October. Gap: 4 September to 4 October. September contributions are included for continuity and do not establish approved billable hours.

# 4. Summary of Key Outputs

Limpopo: Strategic findings and leadership recommendations cover governance, risk ownership, command, Fire Services capability, continuity and community participation. The underlying field visit took place on 15–18 September and predates this reporting window.

CSIR: The 23 September PSA brief defines proposed workstreams, capability allocation, acceptance controls, data governance and cost-model requirements. It provides drafting inputs; PSA signature, final prices and rollout approvals remain to be confirmed.

October: The 9 October workplan links activities to four KRAs, dates, outputs and evidence requirements. The 12 October presentation consolidates progress and the forward programme, with placemarks for missing information. Annexures A1–A5 identify the supporting PoE.

# 5. Detailed Activities Undertaken

## 5.1 Limpopo Catch-up and Report Follow-up

Dates: 2026-09-21 to 2026-09-21 | KRA: KRA 4
Hours: 2 (scheduled) | Status: In progress
Owner: Eng. Dingaan Mahlangu

Output: Limpopo Catch-up and Report Follow-up

Purpose: Coordinate follow-up and record agreed actions.

Strategy and APP alignment: KRA 4: management coordination and reporting.

Evidence: A5 scheduled invitation; attendance unverified

Activity detail: The PoE contains an accepted invitation for the Limpopo catch-up with Dr Tau. The strategic report records capability gaps and recommendations for accountable, tested municipal arrangements.

## 5.2 Limpopo Strategic Report Consolidation

Dates: 2026-09-21 to 2026-09-30 | KRA: KRA 4
Hours: 24 (estimated) | Status: In progress
Owner: Eng. Dingaan Mahlangu

Output: Limpopo strategic report

Purpose: Translate consultation findings into leadership actions.

Strategy and APP alignment: KRA 4: system review and accountable recovery coordination.

Evidence: A1; exact completion date and hours to confirm

Activity detail: The report prepared jointly with Mr Thinus Pretorius provides a leadership synthesis for Musina/Vhembe, Beitbridge and Fetakgomo-Tubatse/Sekhukhune. It recommends named risk owners, capability improvement plans and common SEMS evidence requirements.

## 5.3 NDMC CSIR Agreement Enhancement

Dates: 2026-09-23 to 2026-09-23 | KRA: KRA 4
Hours: 1 (scheduled) | Status: In progress
Owner: Eng. Dingaan Mahlangu

Output: CSIR PSA enhancement brief

Purpose: Define proposed delivery scope and controls.

Strategy and APP alignment: KRA 4: technical integration and NDMC decision rights.

Evidence: A2 and A5; attendance unverified

Activity detail: The PSA brief dated 23 September defines four proposed workstreams and separates CSIR technical delivery from NDMC operational authority. It specifies acceptance gates and cost inputs. The PoE includes the collaboration invitation involving Mr Shafraaz Abdoola and Mr Wiseman Mkhonza. Further engagement occurred telephonically with Mr. Abdoola and some documents were shared.

## 5.4 DM RMO Follow-up Engagement

Dates: 2026-09-22 to 2026-09-22 | KRA: KRA 4
Hours: 4 (scheduled) | Status: In progress
Owner: Eng. Dingaan Mahlangu

Output: DM RMO Follow-up Engagement

Purpose: Coordinate follow-up and record agreed actions.

Strategy and APP alignment: KRA 4: management coordination and reporting.

Evidence: A5 scheduled invitation; attendance unverified

Activity detail: An accepted invitation for the DM-RMO follow-up meeting.

## 5.5 Preparation of the October BBB Workplan

Dates: 2026-10-05 to 2026-10-09 | KRA: KRA 4
Hours: 12 (estimated) | Status: Completed
Owner: Eng. Dingaan Mahlangu

Output: October monthly workplan

Purpose: Schedule dated KRA activities and evidence.

Strategy and APP alignment: KRAs 1–4: monthly delivery and reporting.

Evidence: A3

Activity detail: Prepared the workplan dated 9 October for 5–30 October, aligned to the four KRAs. It covers standards, environmental protection, community readiness, system integration and evidence reporting. Further enhancement and updating of BBB documents and follow ups on standard bodies through E-mail took place.

## 5.6 September October Progress Presentation

Dates: 2026-10-08 to 2026-10-12 | KRA: KRA 4
Hours: 12 (estimated) | Status: Completed
Owner: Eng. Dingaan Mahlangu

Output: September October presentation

Purpose: Summarise progress and anticipated work.

Strategy and APP alignment: KRA 4: management reporting and coordination.

Evidence: A4

Activity detail: Prepared the updated presentation on 12 October, distinguishing September outputs, early-October planning and anticipated work through 31 October. It records the contract gap and missing-information placemarks. This summary and the presentation will be forwarded to Mrs. Ekeke today (13/102026)

# 6. Cross Stream Integration

The Limpopo findings connect BBB recovery planning with SEMS command and reporting arrangements, Fire Services capability, logistics, continuity and civil-society participation. Musina/Beitbridge requires corridor and cross-border coordination; Fetakgomo-Tubatse/Sekhukhune requires adaptation to rural, mining and industrial risks.

The CSIR PSA brief provides a proposed technical interface for damage assessment, GIS and recovery prioritisation alongside climate, logistics/command and wildfire intelligence. NDMC retains operational decisions and acceptance authority.

# 7. Key Lessons Emerging Issues and Risks

Committed people and working relationships need clear authority, funded actions and tested procedures to produce repeatable capability. Main delivery risks are the contract interruption, unverified hours and completion evidence, outstanding site/data selection, stakeholder availability and unresolved CSIR cost and approval requirements. No signed PSA, completed settlement upgrades or conducted community drills are reported as achieved. Monthly status should follow verified outputs rather than planned dates.

# 8. Outputs Against the Workplan

| Output |  | Purpose |  | Contribution to DM RMO Strategy and Matrix and NDMC APP Targets |  | Relevant PoE and status |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Limpopo Catch-up and Report Follow-up | Coordinate follow-up and record agreed actions. | KRA 4 KRA 4: management coordination and reporting. | In progress A5 scheduled invitation; attendance unverified 2 hours (scheduled) |
| Limpopo strategic report | Translate consultation findings into leadership actions. | KRA 4 KRA 4: system review and accountable recovery coordination. | In progress A1; exact completion date and hours to confirm 24 hours (estimated) |
| CSIR PSA enhancement brief | Define proposed delivery scope and controls. | KRA 4 KRA 4: technical integration and NDMC decision rights. | In progress A2 and A5; attendance unverified 1 hours (scheduled) |
| DM RMO Follow-up Engagement | Coordinate follow-up and record agreed actions. | KRA 4 KRA 4: management coordination and reporting. | In progress A5 scheduled invitation; attendance unverified 4 hours (scheduled) |
| October monthly workplan | Schedule dated KRA activities and evidence. | KRA 4 KRAs 1–4: monthly delivery and reporting. | Completed A3 12 hours (estimated) |
| September October presentation | Summarise progress and anticipated work. | KRA 4 KRA 4: management reporting and coordination. | Completed A4 12 hours (estimated) |

# 9. Conclusion

The period produced documented BBB contributions to the Limpopo review, CSIR agreement preparation and October work planning. The next phase should convert these inputs into reviewed technical tools and practical municipal and community guidance. Anticipated outputs for 13–31 October remain subject to available data, stakeholder participation and approvals. October hours are provisionally allocated as 24 retrospective estimated hours and 72 anticipated hours. More work is also being conducted on the Ethekwini pilot document.

# 10. Report Affirmation and Sign Off

I confirm, upon verification and signing below, that this report records my contributions to the Build Back Better (BBB) sub-stream for 21 September 2026 to 12 October 2026. Actual, estimated, scheduled and anticipated hours are identified separately. Evidence references and completion claims must be verified before submission.

Signature __________________
Name: Eng. Dingaan Mahlangu
Date: 2026-10-13

# ANNEXURES

A1. Limpopo Strategic Visit Report prepared jointly by Mr. Dingaan Mahlangu and Mr Thinus Pretorius (field period 15–18 September 2026).

A2. NDMC CSIR PSA Enhancement Brief, Mahlangu, Abdoola and Mkhonza, dated 23 September 2026.

A3. Build Back Better Monthly Workplan October 2026, dated 9 October 2026.

A4. BBB September October Progress and Workplan presentation, prepared 12 October 2026.

A5. September PoE workbook containing accepted invitations dated 21, 22 and 23 September.

A6. Timesheet RMO September 2026 Dingaan and September PoE supplied on 13 October. The timesheet covers 21 August–20 September and records 68 hours.